## Slide 1
PHASE 1 IMPLEMENTATION
ApniLeap Program
Management System
A hub-and-spoke operating model built on Atlassian Cloud — one shared way for ApniLeap and its partner engineering colleges to run, track, and report Phase 1 work.
COEP
MMCOEP
RIT
KLE
Pilot college: COEP → template cloned to MMCOEP, RIT & KLE

## Slide 2
1
THE BIG IDEA
One System, Two Views: Hub & Spoke
Every college does its own work in its own space. The same data automatically rolls up to give ApniLeap leadership the big picture — so nobody has to write reports twice.
ApniLeap HUB
APNI-HUB project
Portfolio & executive dashboard
Cross-college escalations
FIP outcomes view
same
data
COEP
LEAP-COEP · own board + dashboard
MMCOEP
LEAP-MMCOEP · own board + dashboard
RIT
LEAP-RIT · own board + dashboard
KLE
LEAP-KLE · own board + dashboard
Each college is a "spoke" with its own Jira project, dashboard and weekly rhythm — but all four follow the identical template.
Why it matters: Colleges update once. Leadership sees everything. No duplicate reporting.

## Slide 3
2
WHY WE BUILT IT
What Phase 1 Is Trying to Achieve
Live portfolio view
A real-time dashboard showing every college's progress in one place.
Each college in control
Every college gets its own working board and execution dashboard.
One shared language
15 standard workstreams so every college reports the same way.
Track readiness & outcomes
Monitor FIP inputs and outputs leadership can review monthly.
No double reporting
Jira is the single source of truth; Confluence tells the story.
Clear, safe access
Permissions keep each college's sensitive data private.

## Slide 4
3
THE TOOLKIT
The Atlassian Stack Behind It
Phase 1 runs entirely on Atlassian Cloud. Four core tools do the heavy lifting — no custom software needed to start.
Jira
THE EXECUTION ENGINE
Tracks workstreams, action items, risks, blockers, owners and due dates.
Confluence
THE KNOWLEDGE HUB
Holds the executive overview, playbooks, decision logs and meeting notes.
Jira Dashboards
THE LIVE COCKPIT
Hub dashboard plus one repeatable dashboard per college, built from saved filters.
Jira Automation
THE AUTOPILOT
Sends weekly reminders, overdue alerts and escalates blocked items automatically.

## Slide 5
4
STRUCTURE
How Work Is Organised in Jira
Work flows from big goals down to daily tasks — a clear ladder so everyone knows where their piece fits.
Outcome
Goal / Initiative — Improve FIP outcomes for Phase 1 colleges
Workstream
Epic — Faculty Upskilling · Project of Practice · Data & Reporting
Execution item
Task — Validate dashboard fields with the COEP PM
Risk / Decision / Update
Issue, comment or log — Partner data-sharing clause delayed
15 Standard
Workstreams
Governance & Steering
Curriculum Alignment
Faculty Upskilling
Industry Partner Engagement
Student Cohort Formation
Project of Practice
VLSI Center of Excellence
AI Platform Integration
Lab & Infrastructure
Internship & Placement
Assessment & Certification
Communications & Outreach
Data & Reporting
Compliance & Agreements
Scale-up Readiness

## Slide 6
5
VISIBILITY
Two Dashboards, Two Audiences
Hub Dashboard
For ApniLeap core & executives
Phase 1 status across ALL colleges
College-by-college comparison
Blocked, overdue & stale items
FIP inputs: hiring, sign-ups, teams
FIP outputs: projects, IP, placements
Weekly update compliance by college
College Spoke Dashboard
For each college's own team
This college's workstream progress
Open action items by owner & date
Blocked items & asks for ApniLeap
Upcoming milestones & overdue work
Clear ownership: PM, Director, lead
College-specific FIP metrics

## Slide 7
6
THE SMART ASSISTANT
Rovo Agents Read the Dashboards for You
Rovo is Atlassian's built-in AI. It doesn't replace the dashboards — it reads them, summarises what changed, spots missing updates and risks, and drafts review notes. It only ever sees what you're allowed to see.
Tells you what changed
Across ApniLeap and every college, week to week.
Flags problems early
Finds blocked, overdue, stale and sponsor-level items.
Drafts the reports
Weekly portfolio notes and monthly FIP reviews.
Respects boundaries
Never shows one college's private data to another.
One agent per scope — not one agent for everything
Hub agent summarises the whole portfolio. Each college agent is locked to its own project, pages and people. Inside a college, industry-connect sub-agents handle individual partner relationships (MoUs, worklets, mentors) — always asking a human before sending anything partner- or sponsor-facing.

## Slide 8
7
OPERATING RHYTHM
How the Program Runs Each Week
THE MEETING CADENCE
Weekly
College PM update
Action items, risks & asks refreshed
Weekly
ApniLeap cohort checkpoint
Cross-college blockers & playbook fixes
Bi-weekly
Program Director review
College cockpit review & sponsor asks
Monthly
FIP steering review
Inputs, outputs, escalations & decisions
Automation does the chasing
Every Thursday — remind PMs to post updates
Blocked 7 days — alert the ApniLeap lead & escalate
Due date passed — notify owner, flag RAG amber/red
High-severity risk — notify sponsor & core team
Monthly — auto-build the FIP review agenda
Clear, safe access
Each college team edits only its own project
ApniLeap core can see and edit everything
Executives get read-only dashboard views
Sensitive partner / legal data stays restricted

## Slide 9
8
THE PLAN
From Pilot to All Four Colleges
Phase 1 starts small with COEP as the reference model, then copies that proven template to the other colleges.
0
PHASE 0
Licensing & Ownership
2–5 days
Confirm who owns the Atlassian subscription, the discount path and the launch user list.
1
PHASE 1
COEP Pilot
1 week
Build APNI-HUB and LEAP-COEP, set up fields, dashboards and the Confluence hub.
2
PHASE 2
Template Hardening
1 week
Validate the 15 workstreams, tune dashboards and automation, write the playbook.
3
PHASE 3
MMCOEP · RIT · KLE
1–2 weeks
Clone the structure, onboard PMs and get all four colleges reporting the same way.
4
PHASE 4
Scale & Optimise
Ongoing
Add Goals, advanced planning, analytics and new colleges as the program grows.
Phase 1 success looks like: all four colleges reporting in one model, and the monthly FIP review running entirely from live data.

## Slide 10
KEY TAKEAWAYS
What to Remember About Phase 1
Hub-and-spoke model
ApniLeap sees the portfolio; each college runs its own work — on the same data.
COEP leads the way
Prove the template on one college, then clone it to MMCOEP, RIT and KLE.
Atlassian Cloud, no custom build
Jira + Confluence + Dashboards + Automation handle everything in Phase 1.
AI that respects boundaries
Rovo agents summarise and draft, scoped tightly to who is allowed to see what.
Update once, see everywhere
Jira is the single source of truth — no parallel spreadsheets, no double reporting.
Clear finish line
Four colleges live in one model, with a monthly FIP review from real data.